## Sheet1
opgave | Estimeret | Realiseret
Projekt planlægning | 250 | 250
Foranalyse | 300 | 400
Analyse | 300 | 300
Problemformulering | 40 | 80
Projekt bekrivelse | 40 | 40
Projekt mål | 30 | 20
Projekt aktiviteter | 40 | 20
Projekt milepæle | 20 | 10
Projekt Succeskriterier | 20 | 10
Estimeret tidsplan | 70 | 60
Begrundelse for metodevalg og teknologi | 75 | 125
Kravspecifikation | 200 | 300
Design og print af fugleskræmsel | 150 | 380
Test servomotore til fugleskræmsel | 150 | 90
Læs dokumentation på Gravity Analog Dissolved Oxygen Sensor | 30 | 120
Test Gravity Analog Dissolved Oxygen Sensor | 20 | 40
Kalibrering af Gravity Analog Dissolved Oxygen Sensor | 60 | 60
Dokumentation fugleskærmsel (produktblad) | 60
Dokumentation Iltsensor (produktblad) | 60
Design og print af muslingebur | 120
Dokumentation muslingebur (produktblad) | 60
implementering af fugleskræmsel | 160
implementering af iltmåler | 130
implementering af muslingebur | 100
Deployment diagram | 30
Use-case diagram | 60
Decision tree diagram | 60
Flow diagrammer | 70
Arduino circuit diagrammer | 50
UAT | 20

## Sheet2
Realised timeline |  | Points 30 points is approximately 1 hour
Assignment | Total points | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 105 | 110 | 115 | 120 | 125 | 130 | 135 | 140 | 145 | 150 | 155 | 160 | 165 | 170 | 175 | 180 | 185 | 190 | 195 | 200 | 205 | 210 | 215 | 220 | 225 | 230 | 235 | 240 | 245 | 250 | 255 | 260 | 265 | 270 | 275 | 280 | 285 | 290 | 295 | 300 | 305 | 310 | 315 | 320 | 325 | 330 | 335 | 340 | 345 | 350 | 355 | 360 | 365 | 370 | 375 | 380 | 385 | 390 | 395 | 400
Modtag opgave (læs og forstå) | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Projekt planlægning | 250 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 250
Foranalyse | 400
Analyse | 300 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 300
Problemformulering | 80 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 80
Projekt beskrivelse | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Projekt mål | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
Projekt aktiviteter | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
Projekt milepæle | 10 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 10
Projekt Succeskriterier | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 10
Begrundelse for metodevalg og teknologi | 125 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 125
Kravspecifikation | 300 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 300
Design og print af fugleskræmsel | 380
Test servomotore til fugleskræmsel | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Læs dokumentation på Gravity Analog Dissolved Oxygen Sensor | 120
Test Gravity Analog Dissolved Oxygen Sensor | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Kalibrering af Gravity Analog Dissolved Oxygen Sensor | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Dokumentation fugleskærmsel (produktblad)
Dokumentation Iltsensor (produktblad)
Design og print af muslingebur
Dokumentation muslingebur (produktblad)
implementering af fugleskræmsel
implementering af iltmåler
implementering af muslingebur
Deployment diagram
Use-case diagram
Decision tree diagram
Flow diagrammer
Arduino circuit diagrammer
UAT
| Sum points | Points 30 points is approximately 1 hour 5: 2305
| Sum hours | Points 30 points is approximately 1 hour 5: 76.8333