## Sheet1
opgave | Estimeret | Realiseret
Projekt planlægning | 250 | 250
Foranalyse | 300 | 400
Analyse | 300 | 300
Problemformulering | 40 | 80
Projekt bekrivelse | 40 | 40
Projekt mål | 30 | 20
Projekt aktiviteter | 40 | 20
Projekt milepæle | 20 | 10
Projekt Succeskriterier | 20 | 10
Estimeret tidsplan | 70 | 60
Begrundelse for metodevalg og teknologi | 75 | 125
Kravspecifikation | 200 | 300
Design og print af fugleskræmsel | 150 | 380
Test servomotore til fugleskræmsel | 150 | 90
Læs dokumentation på Gravity Analog Dissolved Oxygen Sensor | 30 | 120
Test Gravity Analog Dissolved Oxygen Sensor | 20 | 40
Kalibrering af Gravity Analog Dissolved Oxygen Sensor | 60 | 60
Dokumentation fugleskærmsel (produktblad) | 60
Dokumentation Iltsensor (produktblad) | 60
Design og print af muslingebur | 120
Dokumentation muslingebur (produktblad) | 60
implementering af fugleskræmsel | 160
implementering af iltmåler | 130
implementering af muslingebur | 100
Deployment diagram | 30
Use-case diagram | 60
Decision tree diagram | 60
Flow diagrammer | 70
Arduino circuit diagrammer | 50
UAT | 20

## Sheet2
Estimated timeline |  | Points 30 points is approximately 1 hour
Assignment | Total points | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 105 | 110 | 115 | 120 | 125 | 130 | 135 | 140 | 145 | 150 | 155 | 160 | 165 | 170 | 175 | 180 | 185 | 190 | 195 | 200 | 205 | 210 | 215 | 220 | 225 | 230 | 235 | 240 | 245 | 250 | 255 | 260 | 265 | 270 | 275 | 280 | 285 | 290 | 295 | 300 | 305 | 310 | 315
Modtag opgave (læs og forstå) | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Projekt planlægning | 250 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 250
Foranalyse | 300
Analyse | 300
Problemformulering | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Projekt beskrivelse | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Projekt mål | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Projekt aktiviteter | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Projekt milepæle | 20
Projekt Succeskriterier | 20
Begrundelse for metodevalg og teknologi | 70 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 70
Kravspecifikation | 75 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 75
Design og print af fugleskræmsel | 200 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 200
Test servomotore til fugleskræmsel | 150 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 150
Læs dokumentation på Gravity Analog Dissolved Oxygen Sensor | 150 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 150
Test Gravity Analog Dissolved Oxygen Sensor | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Kalibrering af Gravity Analog Dissolved Oxygen Sensor | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
Dokumentation fugleskærmsel (produktblad) | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Dokumentation Iltsensor (produktblad) | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Design og print af muslingebur | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Dokumentation muslingebur (produktblad) | 120 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 120
implementering af fugleskræmsel | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
implementering af iltmåler | 160 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 160
implementering af muslingebur | 130 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 130
Deployment diagram | 100 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 100
Use-case diagram | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Decision tree diagram | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Flow diagrammer | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Arduino circuit diagrammer | 70 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 70
UAT | 50 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 50
ERD diagram | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
System Sequence diagrams (SSD) | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Make new endpoints in web api | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Update database with new tables | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Make a test outlook email til systemet | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Setup smtp til sende en mail som notification | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Setup api for api key handling | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Mkr1010 setup | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Setup api connection (angular) | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Lav en ny Angular app | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
Sequence diagrams (SD) | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Setup local router | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
Explain docker desktop | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Vælg database | 10 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 10
Vælg user interface | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
Create api project | 10 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 10
Make HTTPGET endpoint to get all measurements | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
Setup entityframeworkCore | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Make HTTPPOST endpoints to create new mesurement | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
Setup database | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Class diagram | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Test endpoints | 20 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 20
Create docker comse file | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Setup and test websocket on webapi | 120 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 120
Make research on how to run docker on raspberry pi | 80 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 80
Make file to docker desktop | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Add Xunit | 60 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 60
Make unittests | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Update Use case diagram | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Klasse diagram fra mail libraryet | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Radegør for i2c I produkt raporten | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Radegør for i2c I process raoprt | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Lav persperviring til process raporten | 30 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 30
Lav konklotion | 40 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 40
Estimated timeline | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Realslerret timeline | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Video | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Video editering | 90 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 90
Klasse diagram fra web api update | 100 | bar: Points 30 points is approximately 1 hour 5 to Points 30 points is approximately 1 hour 100
| Sum points | Points 30 points is approximately 1 hour 5: 4865
| Sum hours | Points 30 points is approximately 1 hour 5: 162.1667